## 2026 Workplan for Members
2026 Workplan
| Jan-Mar 26 | Apr-Jun 26 | Jul-Sep 26 | Oct-Dec 26
Continuous Improvement
CHS Verification and Improvement | Scheme Update - new IV-SA methodology developed. Update other elements of the Scheme (inc Recognition) New Verification support products identified through Verification COP feedback | Scheme Update - development of the new IV-SA methodology. | Scheme Update - Refinement of the methodology of the IV-SA methodology. Continued Verification Support: Identification and development of verification tools and services, including possible AI tools to support Verification, guidelines, CHS mentorship, etc | Scheme Update: Launch of the updated Verification Scheme
Access to Capacity Support | Training - PSEAH Intro and PSEAH for managers. Development of CHS training. IQTS Training. Capacity Services -Governance webinar, IQTS roster Guidance - IQTS children in SEAH investigations | Training - CHS Intro Course/ PSEAH Intro course / IQTS Bangladesh, DRC and Ukraine Capacity Services - Pilot investigation roster, Guidance - Arabic translation of IQTS material | Training- Understanding the CHS Course, PSEAH Managers course (tbc) / Managers training, Development of Accountable Orgs course. Guidance - Investigations with Children guidance published | Training - CHS Intro Course / PSEAH Intro course / IQTS Face to Face training in 3 countries (TBD).
A growing movement for quality and accountability | Membership Growth - Updated Membership material Membership Analysis - Membership Survey / Review of due diligence process and recognition for new members. | Membership Analysis - follow up on survey results New Board Elections | Membership Growth and follow up | General Assembly - Membership Meeting Membership Analysis - Review progress and adapt strategies for the coming year.
Courageous Collaboration
Country level Engagement | CHS Country Cooperatives - start up support. Country capacity strengthening support visits: Afghanistan, DR Congo, Ethiopia, South Sudan, Syria | CHS Country Cooperatives - Support CHS Country Cooperatives to build engagement. Quarterly Learning meeting. | Story gathering: Gather stories to further build CHS Cooperatives momentum Learning: Third learning meeting. | Country Cooperatives: Continued support to establish CHS Country Cooperatives and encourage collective action. Review learning and adapt approach for 2027.
Communities of Practice/ Events | COPs: Verification, PSEAH, Investigators. Other Members Meetings: Donor Recognition Group, Governance circle, Complaint Clinic. Events: HNPW | COPs: Verification, PSEAH, Investigators. Explore demand / feasibility of establishing additional CoP. Other Members Meetings: Complaint Clinic & Donor Recognition Group. | COPs: Verification, PSEAH, Investigators. Other Members Meetings: Complaint Clinic, Donor Recognition Group | COPs: Verification, PSEAH, Investigators. Other Members Meetings: General Assembly, Donor Recognition Group
Partnerships for Innovation | Support to Member led Initiatives: Mapping exercise, design consultations. | Profile member led initiatives and strengthen external partnerships | Profile member led Initiatives and strengthen external partnerships | Review of impact and adapt for coming year.
Collective Action
CHS Due Diligence Endorsement and Passporting | Development of advocacy plan for benefits of CHS passporting. | Mapping and advocacy continued. | Roll out of concerted plans for greater CHS passporting | Review progress made and adapt approach for coming year.
Members Action on PSEAH | HRS - Benefits of HRS package produced for different org types (NNGO, INGO, UN) / PSEAH Donor Round table MDS - Annual Meeting | HRS and MDS - In-country engagements to support analysis and profiling. MDS organisational support. | Info sessions: HRS targeted information sessions. MDS mid-year implementing organisations meeting. | In-country support: HRS continued in-country support. MDS continued organisational support.
Strengthen Sector Wide Approaches to Accountability | Empower: Programme inception phase consultations and start up. | Strengthening Complaints and Investigations - Learning and Review from Collective Assessment | Training and Engagement: Engagement and survivor centred training of Women's Rights Organisations in Bangladesh and Ethiopia. | Strengthening Investigations: Review. Continued engagement with and training of WROs. Co-design of reporting mechanisms.
Informed Influence
Collective Assessments | Preparation: Prepare methodological work for Collective Assessments | Scoping Visits Two Collective Assessments scoping visits | Collective Assessment (subject to funding) | Collective Assessment (subject to funding)
CHS recognition for sector wide impact | Promote and track CHS Recognition | Continued drive for CHS Recognition | Donor and member engagement to track and support promotion. | Review progress with CHS recognition and adapt approach for following year.
Evidence and experienced based advocacy | Humanitarian Accountability Report research & trends analysis. | HAR launch - end of June / July PSEAH - UN and CHS Trends report | HAR engagement events and follow up advocacy. | HAR engagement events and follow up advocacy.